## Sheet1
Sr.No. | Section | Details
1 | Test Plan ID | TP-MM-001
2 | Introduction | This Test Plan For MoneyMate
3 | Objective | Ensure that all functionalities…
4 | Scope of testing | Functional,UI,Database,Security Testing
5 | Test Items | Login,add income,add expance,view history,view Balance
6 | Features to be tested | User Login,Income add,Expance edit,Graph Update
7 | Features not to be tested | UPI integration,Mobile Version
8 | Test Strategy | Manual Testing,Bug testing via Excel
9 | Test Deliverables | Test Cases Documents,bug Report,Final Summary
10 | Testing Tools | Browser dev tools,Postman,Excel
11 | Environments Requeriments | Crome,MongoDB,Spring Boot
12 | Role and Responsibilities | Govind: UI; Partner: Backend
13 | Schedule | Writing: 7 Apr, Execution: 8–9 Apr, Bug Fixing: 10 Apr, Final: 11 Apr
14 | Risks and Mitigation | Internet issue → offline tools, Backend delay → mock data
15 | Entry Criteria | Local deployment, Working modules
16 | Exit Criteria | Major bugs fixed, All test cases passed
17 | Approval | (Leave blank or write “Faculty signature here”)